## Sheet1
User story | estimation | prioritized
As a waiter i want to take an order from customer so that i can take an order to the kitchen | 1 | must
As a founder I want to check the restaurant in-come so that i can check it from the total of order list on that day. | 1 | should
As a chef i want to cook foods from the order lists so that the waiter can take the food to a customer | 1 | low
As a manager i want to check the seats for the customer so that i can book the available seats for customer | 4 | should
As a cashier I want to check bill so that I calculate order list from the customer | 1 | must
As a cashier / waiter I want to edit order list so that I edit order list (cancel food list when customer doesn't have the food) | 7 | should
As a cashier I want to add new order list so that I merge the seats together. | 7 | should
As a manager i want to add new order list so that the waiter can take new order list for customer | 3 | must
As a waiter I want to make a seats for walk-in customer so that the table is unavailable for other. | 4 | must
As a user i want to use this App so that i need to use IOS firmware 10.0 or laster | 1 | should
App stable | 8 | should

## Sheet2
User story | point | prioritized
As a waiter i want to take an order from customer so that i can take an order to the kitchen | 1 | must
As a cashier I want to check bill so that I calculate order list from the customer | 1 | must
As a manager i want to add new order list so that the waiter can take new order list for customer | 3 | must
As a waiter I want to make a seats for walk-in customer so that the table is unavailable for other. | 4 | must
9

## Sheet3
Day | Point planned | Point left | User Story done | Point of user story done
0 | 9 | 9 | 0 | 0
1 | 7 | 8 | 1 | 8
2 | 5 | 8 | 0 | 0
3 | 4 | 6 | 1 | 8
4 | 2 | 5 | 1 | 8
5 | 0 | 5 | 0 | 0